## Risk Register
Risk Analysis & Prioritization - Risk Register
Risk ID | Vulnerability / Risk | CVE / Reference | Affected Asset / Service | Likelihood (1–5) | Impact (1–5) | Risk Score | Risk Level | Risk Justification | Mitigation / Remediation
R-01 | vsftpd Compromised Source Packages Backdoor | CVE-2011-2523 | 192.168.1.3:21 | 5 | 5 | 25 | Critical | Network-accessible FTP service with a documented backdoor; successful exploitation could provide unauthorized root-level access. | Disable/remove compromised vsftpd and replace it with a supported secure file-transfer solution such as SFTP.
R-02 | UnrealIRCd Backdoor | CVE-2010-2075 | 192.168.122.4:6667 | 5 | 5 | 25 | Critical | Week 3 Nessus evidence identified a backdoored UnrealIRCd service with root-level execution. | Disable/remove the compromised service; reinstall only from a trusted source if required and verify integrity.
R-03 | Database Default Credentials (MySQL & PostgreSQL) | Multiple / Configuration Flaw | 192.168.1.3:3306, 5432 | 5 | 5 | 25 | Critical | Network-exposed databases using default or blank credentials could permit unauthorized access without exploiting a software flaw. | Change all default/blank credentials, enforce strong authentication, restrict database access, and review permissions/logs.
R-04 | Apache Tomcat AJP Remote Code Execution (Ghostcat) | CVE-2020-1938 | 192.168.1.3:8009 | 4 | 5 | 20 | Critical | Week 3 report identified an AJP-related vulnerability with potential file disclosure/inclusion and possible code execution depending on configuration. | Validate the exact Tomcat version and scanner evidence, then upgrade to a supported release or disable/restrict AJP if unnecessary.
R-05 | Operating System End of Life (Ubuntu 8.04) | N/A | 192.168.1.3 & 192.168.122.4 | 5 | 5 | 25 | Critical | Unsupported Ubuntu 8.04 lacks vendor security updates, increasing exposure to known weaknesses. | Migrate to a supported OS. Until migration, isolate the legacy host and minimize exposed services.
R-06 | Samba Badlock Vulnerability | CVE-2016-2118 | 192.168.122.4:445 | 3 | 4 | 12 | High | Week 3 report identified a Samba weakness affecting SMB/RPC authentication and potentially shared-resource confidentiality/integrity. | Validate exact Samba version/evidence, patch or upgrade Samba, restrict SMB exposure, and require secure authentication.
R-07 | Unencrypted Legacy R-Services | CVE-1999-0651 | 192.168.1.3:512-514 | 4 | 5 | 20 | Critical | Legacy r-services transmit administrative traffic without modern encryption and increase credential-exposure and unauthorized-access risk. | Disable rexec, rlogin and rsh. Use SSH and restrict administrative access to trusted management hosts.
R-08 | Java RMI Insecure Default Configuration | CVE-2011-3556 | 192.168.1.3:1099 | 3 | 4 | 12 | High | An exposed Java RMI service increases attack surface and may permit unauthorized interaction when insecurely configured. | Restrict RMI to required hosts, disable unnecessary interfaces, apply updates, and review access controls.
R-09 | Web Directory Indexing / Information Disclosure | CWE-548 | 192.168.1.3:80 | 4 | 3 | 12 | High | Nikto identified directory indexing and browsable web content that could disclose files and application structure. | Disable directory listing, remove unnecessary files, restrict documentation/test directories, and review the web root.
R-10 | Outdated Apache/PHP and Web Security Configuration | N/A / Multiple | 192.168.1.3:80 | 4 | 4 | 16 | High | Nikto identified outdated Apache/PHP, HTTP TRACE, and missing security headers, increasing web attack surface. | Upgrade Apache/PHP, disable HTTP TRACE where unnecessary, configure security headers, and retest.